## Onboarding Guide
HSBC ¦ AI PLATFORM
NEW USE CASE ONBOARDING
SSR execution guide ¦ From scratch
PURPOSE
Provide a concise execution path for creating a new AI Platform project/use case, establishing the required access, subscribing to models and reaching the experimentation stage.
CRITICAL DEPENDENCY
The Use Case ADLDS Group must be created before it can be selected/used in the relevant access configuration. The supplied documentation states that the Use Case ADLDS Group is used as the credential identifier when calling the LLM.
Use this workbook as a structured guide — it is intentionally not a tracker. The checkboxes and tables are for reading/printing and execution sequencing, not status management.
1. EXECUTIVE VIEW
STEP | ACTION | OUTCOME
01 | Define use case | Business need and scope
02 | Confirm environment + EIM | Ideation Sandbox or POC
03 | Obtain Use Case ID | UCxxxxxxx
04 | Create Use Case ADLDS Group | infodir-platform-usecase-UCxxxxxxx
05 | Add staff IDs | ADLDS membership
06 | Create project | AI Platform project
07 | Add use case | Use Case under project
08 | Add members | Use Case collaboration
09 | Confirm authentication | Basic / Service Account / Use Case ADLDS
10 | Subscribe models | Model access
11 | Initial test | Model Playground
12 | Develop | API / RAG / Document / Agent Studio
2. SSR ACTION CHECKLIST
DONE | ACTION | EXIT CONDITION
☐ | Confirm Use Case and Use Case ID | ID available
☐ | Confirm environment | Ideation Sandbox / POC
☐ | Confirm EIM | EIM agreed
☐ | Create Use Case ADLDS Group | Group created
☐ | Add required staff IDs | Membership verified
☐ | Create AI Platform Project | Project created
☐ | Add Use Case to Project | Use Case visible
☐ | Add Use Case Members | Team access established
☐ | Confirm API authentication method | Method agreed
☐ | Subscribe required model(s) | Subscription active
☐ | Run initial test | Test successful
3. DETAILED EXECUTION
1. Define the Use Case
• Confirm the use case name and business purpose. • Identify intended environment, users and likely model requirements. • Confirm the use case is ready for onboarding. |  |  | Use Case is agreed and ready to onboard. | Do not proceed until the Use Case ID can be obtained.
2. Confirm Environment and EIM
• Select Ideation Sandbox or POC. • Ideation Sandbox: existing EIM or new EIM can be used. • POC: EIM should be the same EIM registered with the AI Use Case. |  |  | Environment and EIM are agreed. | Do not submit the ADLDS request until the EIM is confirmed.
3. Obtain / Verify Use Case ID
• Obtain the Use Case ID through the documented Group AI / platform process. • Verify that the Use Case ID is visible/recognised in Group AI. |  |  | Use Case ID is available, e.g. UCxxxxxxx. | The ID is required for the documented ADLDS naming convention.
4. Create the Use Case ADLDS Group
• Open the documented ADLDS Group Creation ServiceNow request. • Provide the Business Application EIM. • Create/register the group against the required system. • Naming: infodir-platform-usecase-UCxxxxxxx. |  |  | Use Case ADLDS Group is created and registered. | The group must exist before it can be selected in the relevant access request.
5. Add Staff IDs to the ADLDS Group
• Use the EIM application / ADLDS Access Request process. • Search for the newly created Use Case ADLDS Group. • Add required staff IDs. • Verify membership using the documented mechanism. |  |  | Required team members are members of the ADLDS Group. | Do not assume Project/Use Case membership automatically provides ADLDS access.
6. Create the AI Platform Project
• Create a new project in the AI Platform. • A project can contain a group of use cases. |  |  | Project exists. | Required project-creation permissions are not fully specified in the supplied documentation.
7. Add the Use Case to the Project
• Add the previously created Use Case to the project. • Provide the required use case name, Use Case ID and description. |  |  | Use Case is associated with the project. | Confirm that the Use Case is visible under the project.
8. Add Use Case Members
• Add required users as Use Case Members. • Existing members can collaborate within the assigned project/use case without creating another one. |  |  | Team members can collaborate within the Use Case. | Use Case membership and ADLDS Group membership are separate.
9. Confirm API Authentication
• Review Basic Access, Service Account and Use Case ADLDS. • For API/LLM integration, confirm the required method with the platform team. • Documentation states Use Case ADLDS is the credential identifier when calling the LLM. |  |  | Authentication method is agreed/configured. | The exact mandatory method for this application is not fully specified.
10. Subscribe to Required Models
• Open Model Garden / Marketplace. • Identify required model(s). • Subscribe model(s) to the Use Case. • Obtain platform-admin approval where required. |  |  | Required model subscription is active. | Model availability and approval requirements may vary by environment.
11. Run the Initial Test
• Use Model Playground to test the subscribed model(s). • Run a simple representative test. |  |  | Basic test succeeds. | A successful Playground test is not evidence of production readiness.
12. Move to Required Studio / API Capability
• RAG Studio for RAG pipeline work. • Document Studio for document extraction/classification/analysis. • Agent Studio for agent development. • Use the documented API specification for application integration. |  |  | Required development capability is available. | Studio availability is environment-dependent in the supplied documentation.

## Decisions & Reference
HSBC ¦ AI PLATFORM
DECISIONS, DEPENDENCIES & REFERENCE
4. DEPENDENCY CHAIN
ORDER | DEPENDENCY | PURPOSE
1 | Use Case | Business requirement identified
2 | Use Case ID | Required for downstream identification
3 | Environment + EIM | Onboarding context confirmed
4 | Use Case ADLDS Group | Credential identifier for LLM calls per documentation
5 | Staff IDs | Required users added to ADLDS group
6 | AI Platform Project | Project created
7 | Use Case | Use Case added to project
8 | Use Case Members | Collaboration access
9 | Authentication | API/LLM access route
10 | Model Subscription | Required model available
11 | Testing / Development | Playground / API / Studio
5. ENVIRONMENT AND EIM
ENVIRONMENT | EIM RULE | EVIDENCE STATUS
Ideation Sandbox | Existing EIM or new EIM | Documented Fact
POC | EIM should be the same EIM registered with the AI Use Case | Documented Fact
6. AUTHENTICATION OPTIONS
OPTION | POTENTIAL USE | WHAT THE SUPPLIED DOCUMENTATION ESTABLISHES
Basic Access | Primarily UI usage where API calls are not required | Listed as an option; applicability must be confirmed.
Service Account | Service/API integration | Requires additional setup/provisioning; detailed process is not fully documented.
Use Case ADLDS | Use Case / LLM access | Documentation states it is used as the credential identifier when calling the LLM.
7. DO NOT CONFUSE THESE
ITEM | MEANING / DISTINCTION
Use Case ADLDS Group | Access/credential identity associated with the Use Case.
Platform Access ServiceNow request | Separate platform access process.
AI Platform Project | Container that can contain one or more Use Cases.
Use Case Member | User collaborating within the assigned Use Case.
ADLDS Group Member | Staff ID added to the relevant ADLDS Group.
8. OPEN ITEMS REQUIRING CONFIRMATION
Do not fill these gaps by assumption. Confirm with the relevant AI Platform / Group AI / ADLDS owner before execution.
# | QUESTION TO CONFIRM | OWNER / ANSWER | EVIDENCE / LINK
1 | Who creates the initial AI Use Case?
2 | Who is authorised to create the Use Case ADLDS Group?
3 | Which EIM should be used for the specific POC?
4 | Which authentication option is mandatory for the planned API integration?
5 | What is the ADLDS Group provisioning SLA?
6 | What permissions are required to create Project / Use Case?
7 | Which models are approved/available for the environment?
8 | What approval is required for model subscription?
9. EVIDENCE CLASSIFICATION
CLASSIFICATION | TREATMENT
Documented Fact | Explicitly stated in the supplied AI Platform / Group AI documentation.
Derived / Inferred | Logical dependency or sequencing derived from multiple documented steps.
Unknown | Not specified in the supplied documentation; requires confirmation.
Reference only | User's OneNote research notes are supporting context only, not authoritative evidence.
10. FINAL PRE-SUBMISSION CHECK
DONE | CHECK | STATUS
☐ | Use Case confirmed | Yes / No
☐ | Use Case ID confirmed | Yes / No
☐ | Environment confirmed | Ideation Sandbox / POC
☐ | EIM confirmed | Yes / No
☐ | ADLDS Group naming confirmed | Yes / No
☐ | ADLDS Group created | Yes / No
☐ | Required staff IDs added | Yes / No
☐ | Authentication route confirmed | Yes / No / TBC
Source note: Prepared from the AI Platform / Group AI documentation screenshots supplied in this conversation. The user's OneNote is treated as reference only.