## AI Platform Onboarding
HSBC ¦ AI PLATFORM — NEW USE CASE ONBOARDING
SSR execution sequence ¦ One row = one step
Use this as the single execution sequence. Add the verified ServiceNow / platform URL in the Link column. No unverified URLs have been invented.
Step | What needs to be done | How / Key instruction | Dependency | Expected outcome | Important / TBC | Link | Owner | Status | Planned Date | Notes
1 | Define the Use Case | Confirm business purpose, scope, users and intended AI capability. | None | Use Case is agreed. | Use Case ID will be needed downstream.
2 | Confirm Environment | Decide whether this is Ideation Sandbox or POC. | Step 1 | Environment confirmed. | Environment affects EIM requirements.
3 | Confirm EIM | Ideation Sandbox: existing or new EIM can be used. POC: EIM should be the same EIM registered with the AI Use Case. | Step 2 | EIM confirmed. | Do not guess the EIM.
4 | Obtain / Verify Use Case ID | Obtain the AI Use Case ID and verify it in Group AI. | Step 1 | UCxxxxxxx available. | Required for ADLDS naming.
5 | Create Use Case ADLDS Group | Raise the documented ADLDS Group creation request. Naming: infodir-platform-usecase-UCxxxxxxx. | Steps 3 + 4 | ADLDS Group created and registered. | CRITICAL: documentation states this group is used as the credential identifier when calling the LLM.
6 | Add Staff IDs to ADLDS Group | Use EIM / ADLDS Access Request to add required staff IDs and verify membership. | Step 5 | Required users added. | Project membership does not automatically mean ADLDS membership.
7 | Create AI Platform Project | Create the project in AI Platform. | Steps 1–4 | Project created. | Exact project-creation permissions are not specified.
8 | Add Use Case to Project | Add the Use Case using the Use Case name, ID and description. | Steps 4 + 7 | Use Case appears under Project. | —
9 | Add Use Case Members | Add required team members to the Use Case. | Step 8 | Team can collaborate. | Separate from ADLDS membership.
10 | Confirm Authentication | Confirm whether Basic Access, Service Account or Use Case ADLDS is required for the planned integration. | Steps 5 + 8 | Authentication route agreed. | Confirm with platform team; exact mandatory method is not fully specified.
11 | Subscribe to Models | Open Model Garden / Marketplace and subscribe to required model(s). | Steps 8 + 10 | Model subscription active. | Approval may be required.
12 | Initial Model Test | Test the subscribed model in Model Playground using a simple representative test. | Step 11 | Initial test successful. | Playground success does not establish production readiness.
13 | Development / Integration | Move to API, RAG Studio, Document Studio or Agent Studio as required. | Steps 10–12 | Required development capability available. | Availability may depend on environment.
14 | Readiness Check | Confirm access, approvals, model availability and outstanding dependencies. | Steps 1–13 | Ready to proceed. | Any unresolved TBC must be explicitly recorded.
Note on G4: Paste the verified ServiceNow request URL, platform page, or other relevant documentation link for this step. Do not use an unverified URL.