## Executive Dashboard
HSBC ¦ AI DELIVERY CONTROL TOWER
PROJECT START | 2026-08-17 |  | HARD DEADLINE | NOV 2026 |  | CORE TEAM | 3 |  | PLANNED PEAK TEAM | 5
Overall Health AMBER |  |  |  | Critical Path TBD |  |  |  | Open External Dependencies 10 |  |  | SME Risk HIGH
DELIVERY PRINCIPLE
You are accountable for end-to-end delivery: schedule, quality, technical outcome, stakeholder alignment and recovery. The team cannot use 'code not working' as a delivery escape. Technical issues are delivery issues requiring ownership, recovery and escalation.
TOP DELIVERY CONTROLS
1. Every milestone has one accountable owner and explicit exit criteria.
2. External dependencies are registered from Day 1 with owner, required-by date, trigger and fallback/recovery action.
3. SME availability is a planned dependency; validation cannot be scheduled on an assumed 'TBD' slot.
4. Platform/API/server failures are tracked as delivery dependencies/issues with contingency paths and recovery SLA.
5. October capacity reduction for Durga Puja and November Diwali capacity reduction are explicitly planned into the schedule.
6. Monitoring team owns operational monitoring; IT owns monitoring dashboard build. Delivery team supports both.
7. IT owns deployment/go-live. Delivery team provides support/back-up only; deployment is not a Delivery Lead-owned implementation activity.
KEY MILESTONES
Gate | Milestone | Target Window | Accountable Owner | Dependency | Critical? | Exit Criteria | Status
M1 | Scope & Delivery Baseline | 17–21 Aug | Delivery Lead | Business scope / R&C validation | Yes | Scope, assumptions, plan and governance route agreed | Not Started
M2 | Data Readiness | 24 Aug–4 Sep | Senior Data Scientist | REGMAP/Helios access; data availability | Yes | Coverage, field and quality assessment complete; gaps owned | Not Started
M3 | Linkage Solution Build | 31 Aug–25 Sep | Russel – Senior AI Developer | M2; historical linked dataset | Yes | Candidate methods/prompt/retrieval approaches ready | Not Started
M4 | Linkage Evaluation & Selection | 21 Sep–2 Oct | Delivery Lead + Russel | Golden/evaluation dataset; agreed methodology | Yes | Baseline, evaluation, benchmark and method decision complete | Not Started
M5 | Linkage SME Validation | 5–9 Oct | Delivery Lead | SME availability | Yes | SME validation complete or formal exception/escalation recorded | Not Started
M6 | Impact Assessment Build | 31 Aug–25 Sep | Additional AI Developer* | M2; SME input | Yes | Candidate solution ready for validation | Not Started
M7 | Impact Assessment SME Validation | 5–9 Oct | Delivery Lead | SME availability | Yes | SME validation complete or formal exception/escalation recorded | Not Started
M8 | Production Readiness | 12–23 Oct | Russel + AI Developers | M5/M7; code/documentation/KT | Yes | Code modularised, documented, tested and KT-ready | Not Started
M9 | Monitoring Readiness | 12–30 Oct | Monitoring Team + IT | Monitoring team capacity; IT dashboard | Yes | Monitoring process ready; IT dashboard available/accepted | Not Started
M10 | Governance Approval Gate | 12–30 Oct | Delivery Lead + Sponsor | Governance reviewers / documentation | Yes | Required governance documents/approvals complete | Not Started
M11 | Deployment Readiness | 2–13 Nov | IT (Delivery support) | M8/M9/M10 | Yes | IT confirms deployment readiness | Not Started
M12 | Go-Live | Nov 2026 | IT GHeadache; Delivery Support | M11 | Yes | IT deploys; Delivery validates/supports post-go-live | Not Started
DEADLINE CONTROL
Hard deadline is Nov-2026. Exact day is currently an UNCONFIRMED constraint. Until the contractual/management date is confirmed, the plan uses 13-Nov for operational go-live planning and 20-Nov for post-go-live validation, with recovery capacity reserved.
DELIVERY PLAN VIEW
Use 'Delivery Plan' as the SINGLE SOURCE OF TRUTH. Milestones and activities are on the same sheet. Use the +/- outline controls to collapse all activities for the milestone view or expand only the milestone(s) you are actively managing. Use 'How to Operate' for the operating procedure.
SCHEDULE CONTROL
Delivery Plan now contains Planned, Actual and Forecast dates plus formula-driven working days and predecessor logic. Management Gantt shows milestone-level Planned vs Forecast vs Actual.
M1 / SCOPING STATUS
Scoping is already in progress from 05-Aug-2026 (Delivery Lead + Russel). Management Gantt therefore starts on 05-Aug; the formal remaining project delivery baseline remains controlled through the Delivery Plan.

## How to Operate
HSBC ¦ HOW TO OPERATE THIS DELIVERY CONTROL PLAN
1. PURPOSE OF THIS WORKBOOK
• This workbook is the project control system, not just a task tracker. It is designed to help the Delivery Lead control scope, schedule, quality, resources, dependencies, governance, risks and delivery outcome.
• The 'Delivery Plan' tab is the SINGLE SOURCE OF TRUTH for milestone and activity-level delivery planning. Do not maintain a second copy of the delivery schedule elsewhere.
• The other tabs are control registers that support the Delivery Plan: Executive Dashboard, Resource & Capacity, External Dependency Register, RAID Log, Governance Tracker, Monitoring & Handover, Assumptions & Calendar, RACI, Critical Path and Management Resource Ask.
2. THE DELIVERY PLAN — HOW TO READ IT
• The Delivery Plan has two levels in ONE sheet: MILESTONE rows (M1–M12) and ACTIVITY rows (e.g., M1.1, M1.2, M1.3).
• By default, activities are collapsed. This gives you the 12-milestone management view.
• Use Excel's outline +/- controls on the LEFT side of the sheet to expand or contract the activity rows under each milestone.
• Expand only the milestone you are actively managing. Example: expand M5 during SME validation week; contract M5 again for the management view.
• Do NOT create separate milestone and activity copies. The hierarchy is intentionally designed so one sheet serves both management and execution.
3. DAILY OPERATING MODEL FOR THE DELIVERY LEAD
Start of day | Open Delivery Plan and look at milestone status, Critical Path? and External Dependency? fields.
Then | Expand the milestones that are active in the current 1–2 week window and review their activities.
Control | Check every activity that is due soon: owner, dependency, status, exit criteria and recovery action.
External check | Open External Dependency Register and verify every dependency due within the next 2 weeks has an owner and a credible fallback.
RAID check | Review RAID Log for new risks/issues and confirm every High/Critical item has an owner and action.
Capacity check | Review Resource & Capacity, especially around October Durga Puja and November Diwali availability.
End of day | Update status and comments only where something materially changed; do not turn the plan into a diary.
4. WEEKLY DELIVERY CONTROL — YOUR CORE REVIEW
• 1) Milestones: What moved this week vs plan? What did not?
• 2) Critical path: Has any critical milestone moved to Amber/Red or lost recovery buffer?
• 3) Dependencies: Which external dependency can derail the next 1–2 weeks?
• 4) Resources: Is the team size/capacity still sufficient? Are SME, Monitoring Team or IT resources actually committed?
• 5) Quality: Are deliverables meeting their exit criteria, or are we declaring activities 'done' without evidence?
• 6) Governance: Are documents and approvals progressing in parallel, or becoming end-loaded?
• 7) Recovery: For every Amber/Red item, what is the recovery action, owner and date?
5. HOW TO UPDATE STATUS
• Not Started = work has not begun.
• Green = progressing to plan and exit criteria remain achievable within the planned date.
• Amber = a threat exists to scope/date/quality, but recovery is credible and actively owned.
• Red = milestone/date/quality is materially threatened, blocked or already missed; management action/escalation is required.
• Blocked = work cannot proceed because a dependency or issue is preventing execution.
• Complete = exit criteria are satisfied with evidence. Do not mark Complete merely because the activity was attempted.
6. EXTERNAL DEPENDENCY CONTROL — NON-NEGOTIABLE
• Every material external dependency must be registered BEFORE it becomes a problem.
• Minimum fields: dependency owner, required-by date, failure trigger, impact, preventive control, fallback/recovery action and escalation point.
• Examples: SME availability, REGMAP/Helios data, historical linked-alert data, AI platform, API/quota, server/compute, Monitoring Team, IT dashboard, governance reviewers, Model Sponsor and IT deployment.
• If the dependency has no named owner, treat it as an unresolved delivery risk — not as an invisible assumption.
• If the required-by date is approaching and the dependency is not confirmed, move the related activity to Amber and trigger the recovery/escalation path.
7. SME AVAILABILITY CONTROL
• SME validation is a schedule dependency, not an informal request for help.
• Book M5 and M7 validation slots from the beginning of the project; identify a backup SME/delegate.
• If the SME does not attend or no SME is provided, do NOT silently move the milestone. Record the dependency failure, assess critical-path impact, escalate and invoke the documented fallback.
• A validation milestone is complete only when SME validation/sign-off is completed OR a formally approved exception/decision is recorded.
8. PLATFORM / API / SERVER FAILURE CONTROL
• Platform/API/server availability is treated as an external delivery dependency.
• The team should maintain test artefacts/cached test cases and use approved alternate compute/model/API options where permitted.
• When an outage occurs: log the issue → quantify schedule impact → invoke fallback → re-sequence non-dependent work → escalate if the recovery threshold is exceeded.
• Do not hide infrastructure outages inside a generic 'development delay'. The failure and its delivery impact must be visible.
9. GOVERNANCE OPERATING MODEL
• Governance documentation is created progressively, not at the end.
• Track ASDA, Monitoring documentation, MDT, ToR, QMIO, AIRCO and IMR as explicit activities in the Governance Tracker.
• AIRCO requires additional Delivery Lead effort: prepare the document/evidence pack, arrange the Model Sponsor walkthrough, spoon-feed the sponsor through responsibilities/evidence, and track open actions to closure.
• If a governance reviewer is unavailable, record the dependency and escalate rather than allowing an invisible date slip.
10. MONITORING AND DEPLOYMENT BOUNDARIES
• Monitoring Team owns operational monitoring/KPI execution. Your team supports with solution context, KPI definition and handover.
• IT owns the monitoring dashboard build. Your team provides requirements and validates the dashboard.
• IT owns deployment and Go-Live. Your team remains available for technical/business support and back-up, but deployment execution is not your team's responsibility.
• This boundary is reflected in the RACI. Do not allow ownership to drift during execution.
11. RESOURCE & CAPACITY CONTROL
• Core confirmed team: Delivery Lead + Russel (Senior AI Developer) + Junior Data Scientist/AI Developer.
• The plan recommends additional Data Scientist/AI Developer capacity because two AI solution tracks must progress in parallel and Russel is otherwise a technical single point of failure.
• October capacity must reflect Durga Puja leave for Kolkata-based team members. Confirm exact leave dates and update Resource & Capacity.
• November must reflect Diwali availability risk. Confirm the support rota before deployment/go-live.
• Do not solve a resource shortfall by quietly extending the deadline — the deadline is a hard constraint.
12. RACI — HOW TO USE IT
• R = Responsible: executes the work. A = Accountable: owns the outcome. C = Consulted: provides input. I = Informed: needs visibility.
• Apply the rule: ONE accountable owner per deliverable. Do not create multiple 'A' owners for the same outcome.
• Your overall role is Delivery Lead / Delivery Owner. You are accountable for the project's delivery outcome, but external execution ownership remains with IT/Monitoring where explicitly assigned.
13. CRITICAL PATH — HOW TO USE IT
• Review the Critical Path at least weekly and before every management status update.
• If a critical-path milestone slips, immediately determine whether there is remaining schedule float, then define a recovery action and owner.
• Do not wait for the milestone date to be missed before escalating. Escalate when the remaining recovery buffer becomes insufficient.
14. MANAGEMENT RESOURCE ASK
• Use the Management Resource Ask tab when requesting additional team members.
• The argument is based on delivery capacity and risk: parallel Linkage + Impact Assessment work, technical bottleneck, hard Nov deadline, October/November capacity loss and external dependency uncertainty.
• Recommended position: 5-person peak delivery capacity; 4 people is the minimum acceptable position if Management will not approve 2 additional resources.
15. WHAT 'DONE' MEANS
• An activity is not Done because someone says it is done. Its exit/acceptance criteria must be satisfied.
• A milestone is not Done until its required activities and gate evidence are complete, dependencies resolved/accepted, and the milestone exit criteria are met.
• A Red/Blocked item cannot be hidden by marking downstream work Complete.
• The Delivery Lead should be able to answer at any time: Where are we? Where should we be? What is blocking us? What happens next? Who owns it? By when?
16. LIVE SCHEDULE CONTROL — PLANNED vs ACTUAL vs FORECAST
• Planned Start/End are the approved baseline; preserve them so variance remains visible.
• Actual Start/End are manually entered facts when work actually starts/finishes.
• Planned Working Days and Actual Working Days are formula-driven using Schedule Calendar.
• Forecast Start/End are the current delivery expectation; a delayed predecessor pushes downstream forecast dates.
• Milestone Planned dates are calculated from child activities; milestone Actual/Forecast dates roll up from child dates.
• Use Predecessor(s) to explicitly connect sequencing. Do not hide dependencies in comments.
• Do not overwrite baseline Planned dates to hide slippage; re-baseline only with explicit management decision.
17. WHEN SOMETHING SLIPS
• Record the issue/event; enter Actual dates when known and update Status/Risk.
• Review Forecast dates for the affected activity and downstream dependencies.
• Check whether the milestone forecast moved beyond its planned end.
• If Critical Path = Yes, define recovery and escalate before the hard deadline is threatened.
• Record the blocker in External Dependency Register or RAID Log.
18. MANAGEMENT GANTT
• Use Management Gantt for weekly management/SteerCo discussion.
• Blue = Planned baseline; pale red = current Forecast; HSBC red = Actual.
• Use Delivery Plan for drill-down and task-level control.
• Predecessor(s) must contain milestone/activity IDs (e.g., M2.1, M2.2, M4). If a predecessor finishes late, the dependent activity's Forecast Start automatically moves to the next working day after the latest predecessor forecast end.
19. MILESTONE DATE ROLL-UP RULE
• Planned Start for a milestone = MINIMUM Planned Start of all its child activities.
• Planned End for a milestone = MAXIMUM Planned End of all its child activities.
• If all child dates are blank, the milestone remains blank — never 00-Jan-1900.
• The Management Gantt begins on 05-Aug-2026 because M1 scoping is already in progress. The remaining delivery baseline can still be controlled from the formal project start of 17-Aug-2026.

## Delivery Plan
HSBC ¦ DELIVERY PLAN — LIVE SCHEDULE CONTROL
ID | Workstream | Milestone / Activity | Accountable Owner | Predecessor(s) | Planned Start | Planned End | Planned Working Days | Actual Start | Actual End | Actual Working Days | Forecast Start | Forecast End | Forecast Working Days | Exit / Acceptance Criteria | Status | Critical Path? | External Dependency? | Contingency / Recovery Action | Leave / Capacity Impact | Risk / Issue | Comments
M1 | Scope | Scope & Delivery Baseline | Delivery Lead |  | 2026-08-05 | [5 empty] | 2026-08-05 | 2026-09-24 | 37 | Milestone exit criteria defined in the operating model | Green | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact | Scoping document currently in progress; Delivery Lead + Russel are drafting. | Gantt starts 05-Aug-2026 to reflect work already underway.
M1.1 | Scope | Scope document sign-off | Delivery Lead |  | 2026-08-05 | 19-Aug-26 | 11 |  |  |  | 2026-08-05 | 2026-08-19 | 11 | Scope and objectives approved | Not Started | Yes | Yes | Escalate same day if required stakeholder unavailable; document decision/assumption and protect baseline. | None
M1.2 | Scope | R&C Impact Assessment outcome validation | Delivery Lead | M1.1 | 2026-08-05 | 21-Aug-26 | 13 |  |  |  | 2026-08-20 | 2026-09-07 | 13 | Outcome validated and open questions assigned | Not Started | Yes | Yes | Pre-book stakeholder session; nominate delegate if primary unavailable. | None
M1.3 | Scope | Delivery baseline, RAID and dependency register | Delivery Lead | M1.1, M1.2 | 2026-08-05 | 21-Aug-26 | 13 |  |  |  | 2026-09-08 | 2026-09-24 | 13 | Integrated plan, RAID and dependency controls live | Not Started | Yes | No | N/A | None
M2 | EDA | Data Readiness | Senior Data Scientist | M1 | [6 empty] | 2026-09-25 | 2026-10-28 | 24 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M2.1 | EDA | REGMAP EDA | Senior Data Scientist / Junior Data Scientist | M1 | 24-Aug-26 | 28-Aug-26 | 5 |  |  |  | 2026-09-25 | 2026-10-01 | 5 | EDA complete; usable population quantified | Not Started | Yes | Yes | Escalate access; use approved alternative extract if available; re-sequence non-dependent work. | None
M2.2 | EDA | Helios EDA | Senior Data Scientist / Junior Data Scientist | M2.1 | 24-Aug-26 | 28-Aug-26 | 5 |  |  |  | 2026-10-02 | 2026-10-08 | 5 | EDA complete; usable population quantified | Not Started | Yes | Yes | Same as M2.1. | None
M2.3 | EDA | Data coverage assessment | Junior Data Scientist | M2.1, M2.2 | 31-Aug-26 | 1-Sep-26 | 2 |  |  |  | 2026-10-09 | 2026-10-12 | 2 | Coverage and missingness quantified | Not Started | Yes | No | Use available extracts; clearly flag coverage gaps. | None
M2.4 | EDA | Data field validation | Junior Data Scientist | M2.1, M2.2 | 31-Aug-26 | 2-Sep-26 | 3 |  |  |  | 2026-10-09 | 2026-10-13 | 3 | Required fields validated | Not Started | Yes | No | Prioritise critical fields; raise gap decisions immediately. | None
M2.5 | EDA | Data quality assessment | Senior Data Scientist | M2.1, M2.2 | 1-Sep-26 | 4-Sep-26 | 4 |  |  |  | 2026-10-09 | 2026-10-14 | 4 | Quality issues quantified and owners assigned | Not Started | Yes | No | Create data-quality exception list; do not silently proceed. | None
M2.6 | EDA | Historical linked-alert / labelled dataset readiness | Delivery Lead + Senior Data Scientist | M2.5 | 24-Aug-26 | 4-Sep-26 | 10 |  |  |  | 2026-10-15 | 2026-10-28 | 10 | Sufficient historical linked examples available or explicit limitation accepted | Not Started | Yes | Yes | Escalate as Day-1 critical dependency; if unavailable, formally document inability to establish credible baseline/evaluation and re-plan decision. | None
M3 | Linkage | Linkage Solution Build | Russel – Senior AI Developer | M2 | [6 empty] | 2026-10-29 | 2026-12-18 | 37 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M3.1 | Linkage | Embedding solution development | Russel – Senior AI Developer | M2 | 31-Aug-26 | 11-Sep-26 | 10 |  |  |  | 2026-10-29 | 2026-11-11 | 10 | Candidate embedding approaches implemented | Not Started | Yes | No | Use alternative approved approach if platform/API unavailable; maintain experiment log. | None
M3.2 | Linkage | Model training / candidate modelling | Russel + AI Developer* | M2 | 7-Sep-26 | 18-Sep-26 | 10 |  |  |  | 2026-10-29 | 2026-11-11 | 10 | Candidate models trained and reproducible | Not Started | Yes | Yes | Use approved alternate compute environment; queue jobs; escalate capacity outage. | None
M3.3 | Linkage | GenAI solution development | Russel + AI Developer* | M3.2 | 7-Sep-26 | 18-Sep-26 | 10 |  |  |  | 2026-11-12 | 2026-11-25 | 10 | Candidate GenAI approach operational in test environment | Not Started | Yes | Yes | Maintain fallback model/API where approved; if service outage > agreed threshold, switch to offline testing/review. | None
M3.4 | Linkage | Prompt engineering | AI Developer* + Russel | M3.3 | 10-Sep-26 | 18-Sep-26 | 7 |  |  |  | 2026-11-26 | 2026-12-04 | 7 | Prompt iterations documented with test results | Not Started | Yes | No | Continue prompt design using cached/test data if live API unavailable. | None
M3.5 | Linkage | Retrieval tuning | AI Developer* + Russel | M3.4 | 14-Sep-26 | 25-Sep-26 | 10 |  |  |  | 2026-12-07 | 2026-12-18 | 10 | Retrieval configuration tuned and evaluated | Not Started | Yes | Yes | Use offline/indexed test set; restore/rebuild index if service fails. | None
M4 | Linkage | Evaluation & Method Selection | Delivery Lead | M3 | [6 empty] | 2026-12-21 | 2027-01-06 | 13 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M4.1 | Linkage | Evaluation of multiple methods | Delivery Lead + Russel | M3 | 21-Sep-26 | 29-Sep-26 | 7 |  |  |  | 2026-12-21 | 2026-12-29 | 7 | All candidate methods evaluated against agreed methodology | Not Started | Yes | Yes | If dataset/SME unavailable, escalate as decision blocker; no unsupported claim of performance. | None
M4.2 | Linkage | Cross-method benchmarking | Senior Data Scientist | M4.1 | 28-Sep-26 | 1-Oct-26 | 4 |  |  |  | 2026-12-30 | 2027-01-04 | 4 | Comparative benchmark completed | Not Started | Yes | No | Use fixed evaluation set and documented metrics. | None
M4.3 | Linkage | Final method selection | Delivery Lead | M4.1, M4.2 | 1-Oct-26 | 2-Oct-26 | 2 |  |  |  | 2027-01-05 | 2027-01-06 | 2 | Decision documented with evidence and trade-offs | Not Started | Yes | No | Escalate decision if evidence is insufficient; do not select based on preference. | None
M5 | Linkage | SME Validation / Sign-off | Delivery Lead | M4 | [6 empty] | 2027-01-07 | 2027-01-15 | 7 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M5.1 | Linkage | SME validation session | Delivery Lead | M4 | 5-Oct-26 | 6-Oct-26 | 2 |  |  |  | 2027-01-07 | 2027-01-08 | 2 | SME review completed and findings logged | Not Started | Yes | Yes | SME slot pre-booked from Aug; named backup SME/delegate; escalate no-show immediately. | Durga Puja leave window begins mid-Oct
M5.2 | Linkage | SME findings remediation | Russel + AI Developer* | M5.1 | 6-Oct-26 | 8-Oct-26 | 3 |  |  |  | 2027-01-11 | 2027-01-13 | 3 | Material findings addressed or formally accepted | Not Started | Yes | Yes | Reserve remediation capacity before Puja; unresolved findings escalated to sponsor. | Durga Puja leave window
M5.3 | Linkage | Final SME sign-off / exception record | Delivery Lead | M5.2 | 8-Oct-26 | 9-Oct-26 | 2 |  |  |  | 2027-01-14 | 2027-01-15 | 2 | Signed validation or documented exception with decision owner | Not Started | Yes | Yes | Delegate approval or sponsor escalation; no silent carry-over. | Durga Puja leave window
M6 | Impact Assessment | Impact Assessment Build | AI Developer* + Russel | M5 | [6 empty] | 2026-10-29 | 2026-12-02 | 25 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M6.1 | Impact Assessment | GenAI solution development | AI Developer* + Russel | M2 | 31-Aug-26 | 18-Sep-26 | 15 |  |  |  | 2026-10-29 | 2026-11-18 | 15 | Candidate solution ready | Not Started | Yes | Yes | Fallback approved environment / offline testing during outage. | None
M6.2 | Impact Assessment | Prompt engineering | AI Developer* | M6.1 | 7-Sep-26 | 18-Sep-26 | 10 |  |  |  | 2026-11-19 | 2026-12-02 | 10 | Prompt iterations documented | Not Started | Yes | No | Use cached test cases if API unavailable. | None
M6.3 | Impact Assessment | Retrieval tuning | AI Developer* | M6.1 | 14-Sep-26 | 25-Sep-26 | 10 |  |  |  | 2026-11-19 | 2026-12-02 | 10 | Retrieval tuned and tested | Not Started | Yes | Yes | Offline/index rebuild fallback. | None
M7 | Impact Assessment | SME Validation / Sign-off | Delivery Lead | M6 | [6 empty] | 2026-12-03 | 2026-12-11 | 7 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M7.1 | Impact Assessment | SME validation | Delivery Lead | M6 | 5-Oct-26 | 6-Oct-26 | 2 |  |  |  | 2026-12-03 | 2026-12-04 | 2 | SME validation completed | Not Started | Yes | Yes | Pre-booked slot + backup SME + sponsor escalation. | Durga Puja leave window begins mid-Oct
M7.2 | Impact Assessment | Remediation | AI Developer* + Russel | M7.1 | 6-Oct-26 | 8-Oct-26 | 3 |  |  |  | 2026-12-07 | 2026-12-09 | 3 | Material findings addressed / accepted | Not Started | Yes | Yes | Protect capacity before Puja. | Durga Puja leave window
M7.3 | Impact Assessment | Documentation and final sign-off | Delivery Lead | M7.2 | 8-Oct-26 | 9-Oct-26 | 2 |  |  |  | 2026-12-10 | 2026-12-11 | 2 | Validation evidence and sign-off complete | Not Started | Yes | No | Sponsor escalation for unresolved sign-off. | Durga Puja leave window
M8 | Productionization | Production Readiness | Russel – Senior AI Developer | M7 | [6 empty] | 2027-01-18 | 2027-02-10 | 18 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M8.1 | Productionization | Code modularization | Russel – Senior AI Developer | M5, M7 | 12-Oct-26 | 20-Oct-26 | 7 |  |  |  | 2027-01-18 | 2027-01-26 | 7 | Modular, maintainable code baseline complete | Not Started | Yes | No | Prioritise critical modules; protect post-Puja catch-up capacity. | Durga Puja / reduced Kolkata capacity
M8.2 | Productionization | Code documentation | Junior Data Scientist + AI Developers | M8.1 | 12-Oct-26 | 21-Oct-26 | 8 |  |  |  | 2027-01-27 | 2027-02-05 | 8 | Technical documentation complete and current | Not Started | Yes | No | Documentation starts during development; do not defer all documentation to end. | Durga Puja / reduced Kolkata capacity
M8.3 | Productionization | Code KT to Tech team | Russel + Delivery Lead | M8.1, M8.2 | 21-Oct-26 | 23-Oct-26 | 3 |  |  |  | 2027-02-08 | 2027-02-10 | 3 | KT completed; open technical questions logged | Not Started | Yes | Yes | Pre-book Tech slots; provide recorded walkthrough if attendance fails. | Post-Puja capacity recovery
M9 | Monitoring | Monitoring Readiness | Monitoring Team + IT | M8 | [6 empty] | 2027-02-11 | 2027-03-12 | 22 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M9.1 | Monitoring | Monitoring requirements / KPI definition | Delivery Lead + Monitoring Team | M8 | 12-Oct-26 | 16-Oct-26 | 5 |  |  |  | 2027-02-11 | 2027-02-17 | 5 | KPIs, thresholds, ownership and escalation path agreed | Not Started | Yes | Yes | Secure Monitoring Team commitment in Aug; named backup; escalate capacity gap. | Durga Puja capacity impact
M9.2 | Monitoring | Monitoring document | Delivery Lead + Monitoring Team | M9.1 | 15-Oct-26 | 21-Oct-26 | 5 |  |  |  | 2027-02-18 | 2027-02-24 | 5 | Monitoring document approved | Not Started | Yes | Yes | Draft in parallel with KPI definition. | Durga Puja capacity impact
M9.3 | Monitoring | Monitoring dashboard build | IT | M9.1 | 15-Oct-26 | 30-Oct-26 | 12 |  |  |  | 2027-02-18 | 2027-03-05 | 12 | IT dashboard available and validated | Not Started | Yes | Yes | Escalate IT capacity; agree interim manual monitoring if dashboard delayed. | Durga Puja capacity impact
M9.4 | Monitoring | Monitoring team handover / support | Delivery Team + Monitoring Team | M9.2, M9.3 | 26-Oct-26 | 30-Oct-26 | 5 |  |  |  | 2027-03-08 | 2027-03-12 | 5 | Monitoring team accepts operational responsibility; Delivery remains support | Not Started | Yes | Yes | Named operational owner and backup confirmed. | Post-Puja
M10 | Governance | Governance Approval Gate | Delivery Lead | M9 | [6 empty] | 2027-02-25 | 2027-04-27 | 44 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M10.1 | Governance | ASDA documentation | Delivery Lead + relevant owners | M9 | 12-Oct-26 | 19-Oct-26 | 6 |  |  |  | 2027-03-15 | 2027-03-22 | 6 | ASDA document complete/submitted | Not Started | Yes | Yes | Pre-agree reviewer slots; track comments to closure. | Durga Puja capacity impact
M10.2 | Governance | Monitoring documentation for governance | Delivery Lead + Monitoring Team | M9.1, M9.2 | 12-Oct-26 | 21-Oct-26 | 8 |  |  |  | 2027-02-25 | 2027-03-08 | 8 | Monitoring evidence/document complete | Not Started | Yes | Yes | Build in parallel; avoid end-loaded documentation. | Durga Puja capacity impact
M10.3 | Governance | MDT documentation | Delivery Lead + relevant owners | M10.2 | 19-Oct-26 | 23-Oct-26 | 5 |  |  |  | 2027-03-09 | 2027-03-15 | 5 | MDT document complete/submitted | Not Started | Yes | Yes | Pre-book review; delegate if needed. | Durga Puja / reduced Kolkata capacity
M10.4 | Governance | ToR documentation | Delivery Lead | M10.3 | 19-Oct-26 | 23-Oct-26 | 5 |  |  |  | 2027-03-16 | 2027-03-22 | 5 | ToR complete/submitted | Not Started | Yes | No | Prepare template early. | Durga Puja / reduced Kolkata capacity
M10.5 | Governance | AIRCO documentation | Delivery Lead + Model Sponsor | M10.4 | 19-Oct-26 | 28-Oct-26 | 8 |  |  |  | 2027-03-23 | 2027-04-01 | 8 | AIRCO pack completed and handed over with sponsor walkthrough | Not Started | Yes | Yes | Pre-book sponsor; spoon-feed walkthrough and evidence pack; maintain action tracker to closure. | Durga Puja / reduced Kolkata capacity
M10.6 | Governance | QMIO documentation | Delivery Lead + relevant owners | M10.5 | 19-Oct-26 | 28-Oct-26 | 8 |  |  |  | 2027-04-02 | 2027-04-13 | 8 | QMIO document complete/submitted | Not Started | Yes | Yes | Pre-book reviewers; resolve comments daily. | Durga Puja / reduced Kolkata capacity
M10.7 | Governance | IMR approval documentation | Delivery Lead + relevant owners | M10.6 | 19-Oct-26 | 30-Oct-26 | 10 |  |  |  | 2027-04-14 | 2027-04-27 | 10 | IMR evidence/approval complete as applicable | Not Started | Yes | Yes | Start evidence collection before October; avoid first draft in governance window. | Durga Puja / reduced Kolkata capacity
M11 | Deployment | Deployment Readiness | IT (Delivery support) | M10 | [6 empty] | 2027-04-28 | 2027-05-11 | 10 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M11.1 | Deployment | IT deployment readiness | IT | M8, M9, M10 | 2-Nov-26 | 6-Nov-26 | 5 |  |  |  | 2027-04-28 | 2027-05-04 | 5 | IT confirms prerequisites satisfied | Not Started | Yes | Yes | Escalate IT blocker; Delivery provides evidence/support. | None
M11.2 | Deployment | Delivery support / back-up readiness | Delivery Lead + Russel | M11.1 | 2-Nov-26 | 6-Nov-26 | 5 |  |  |  | 2027-05-05 | 2027-05-11 | 5 | Support rota and escalation contacts confirmed | Not Started | Yes | No | Pre-agree support window around Diwali. | Diwali / reduced capacity risk
M12 | Deployment | Go-Live | IT (Delivery support) | M11 | [6 empty] | 2027-05-12 | 2027-06-01 | 15 | Milestone exit criteria defined in the operating model | Not Started | Yes | Yes | See External Dependency Register / RAID Log | October Durga Puja + November Diwali capacity impact
M12.1 | Deployment | Production deployment | IT | M11 | 9-Nov-26 | 13-Nov-26 | 5 |  |  |  | 2027-05-12 | 2027-05-18 | 5 | IT deploys successfully | Not Started | Yes | Yes | IT owns deployment recovery plan; Delivery supports technical/business clarification. | Diwali recovery window
M12.2 | Deployment | Post-go-live validation and support | Delivery Lead + Russel | M12.1 | 9-Nov-26 | 20-Nov-26 | 10 |  |  |  | 2027-05-19 | 2027-06-01 | 10 | Business/technical validation complete; issues owned and transitioned | Not Started | Yes | No | Prioritised support rota; escalate material production issues. | Post-Diwali
Formulas:
Planned Start = IF(COUNT([Planned Start, row below]:F7)=0,"",MIN([Planned Start, row below]:F7))
Planned Working Days = IF(OR([Planned Start]="",[Planned End]=""),"",NETWORKDAYS.INTL([Planned Start],[Planned End],1,'Schedule Calendar'!$H6:H30))
Actual Working Days = IF(OR([Actual Start]="",[Actual End]=""),"",NETWORKDAYS.INTL([Actual Start],[Actual End],1,'Schedule Calendar'!$H6:H30))
Forecast Start = IFERROR(MIN([Forecast Start, row below]:L7),"")
Forecast Start = IF([Actual Start]<>"",[Actual Start],[Planned Start])
Forecast End = IFERROR(MAX([Forecast End, row below]:M7),"")
Forecast End = IF([Actual End]<>"",[Actual End],IF(OR([Forecast Start]="",[Planned Working Days]=""),"",WORKDAY([Forecast Start],[Planned Working Days]-1,'Schedule Calendar'!$H6:H30)))
Forecast Working Days = IF(OR([Forecast Start]="",[Forecast End]=""),"",NETWORKDAYS.INTL([Forecast Start],[Forecast End],1,'Schedule Calendar'!$H6:H30))

## Management Gantt
HSBC ¦ MANAGEMENT GANTT — PLANNED vs FORECAST vs ACTUAL
ID | Milestone | Owner | Planned Start | Planned End | Forecast Start | Forecast End | Actual Start | Actual End | Status | Critical? | time axis 2026-08-05 to 2026-11-30
M1 | Scope & Delivery Baseline | Delivery Lead | 2026-08-05 |  | 2026-08-05 | 2026-09-24 |  | 0 | Green | Yes
M2 | Data Readiness | Senior Data Scientist |  |  | 2026-09-25 | 2026-10-28 |  | 0 | Not Started | Yes
M3 | Linkage Solution Build | Russel – Senior AI Developer |  |  | 2026-10-29 | 2026-12-18 |  | 0 | Not Started | Yes
M4 | Evaluation & Method Selection | Delivery Lead |  |  | 2026-12-21 | 2027-01-06 |  | 0 | Not Started | Yes
M5 | SME Validation / Sign-off | Delivery Lead |  |  | 2027-01-07 | 2027-01-15 |  | 0 | Not Started | Yes
M6 | Impact Assessment Build | AI Developer* + Russel |  |  | 2026-10-29 | 2026-12-02 |  | 0 | Not Started | Yes
M7 | SME Validation / Sign-off | Delivery Lead |  |  | 2026-12-03 | 2026-12-11 |  | 0 | Not Started | Yes
M8 | Production Readiness | Russel – Senior AI Developer |  |  | 2027-01-18 | 2027-02-10 |  | 0 | Not Started | Yes
M9 | Monitoring Readiness | Monitoring Team + IT |  |  | 2027-02-11 | 2027-03-12 |  | 0 | Not Started | Yes
M10 | Governance Approval Gate | Delivery Lead |  |  | 2027-02-25 | 2027-04-27 |  | 0 | Not Started | Yes
M11 | Deployment Readiness | IT (Delivery support) |  |  | 2027-04-28 | 2027-05-11 |  | 0 | Not Started | Yes
M12 | Go-Live | IT (Delivery support) |  |  | 2027-05-12 | 2027-06-01 |  | 0 | Not Started | Yes
Legend
Planned
Forecast
Actual
MANAGEMENT RULE
Forecast beyond Planned End = schedule variance. Actual End beyond Planned End = realised variance. M1 scoping is already in progress from 05-Aug-2026.

## Schedule Calendar
HSBC ¦ SCHEDULE CALENDAR & NON-WORKING DAYS
Date | Day | Working Day? | Reason / Holiday / Leave | Project-wide Non-Working? | Notes | Project-wide Non-Working Dates
2026-08-17 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity. | Date | Reason
2026-08-18 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-19 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-20 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-21 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-22 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-23 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-24 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-25 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-26 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-27 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-28 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-29 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-30 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-08-31 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-01 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-02 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-03 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-04 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-05 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-06 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-07 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-08 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-09 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-10 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-11 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-12 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-13 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity. | Only enter project-wide non-working dates here. Individual Durga Puja / Diwali leave is tracked in Resource & Capacity and should not automatically stop the project calendar.
2026-09-14 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-15 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-16 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-17 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-18 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-19 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-20 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-21 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-22 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-23 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-24 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-25 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-26 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-27 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-28 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-29 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-09-30 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-01 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-02 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-03 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-04 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-05 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-06 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-07 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-08 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-09 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-10 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-11 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-12 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-13 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-14 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-15 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-16 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-17 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-18 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-19 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-20 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-21 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-22 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-23 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-24 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-25 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-26 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-27 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-28 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-29 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-30 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-10-31 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-01 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-02 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-03 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-04 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-05 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-06 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-07 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-08 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-09 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-10 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-11 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-12 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-13 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-14 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-15 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-16 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-17 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-18 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-19 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-20 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-21 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-22 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-23 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-24 | Tuesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-25 | Wednesday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-26 | Thursday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-27 | Friday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-28 | Saturday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-29 | Sunday | No |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.
2026-11-30 | Monday | Yes |  | No | Project-wide closure only; individual leave remains in Resource & Capacity.

## Resource & Capacity
HSBC ¦ RESOURCE & CAPACITY
Resource | Role | Confirmed? | Start | Primary Accountability | Aug Capacity | Sep Capacity | Oct Capacity | Nov Capacity | Peak Need | Management Ask
You | Delivery Lead / Delivery Owner | Yes | 17-Aug-26 | End-to-end delivery, QC, schedule, RAID, governance, stakeholder management, recovery; hands-on where required | 100% | 100% | 85%* | 100% | Critical | N/A – existing core role
Russel | Senior AI Developer | Yes | 17-Aug-26 | Technical lead, architecture, core AI development, evaluation, code quality, production readiness | 100% | 100% | 85%* | 100% | Critical | N/A – existing core role
Junior Developer | Junior Data Scientist / AI Developer | Yes | 17-Aug-26 | EDA, data preparation, testing, documentation, support to development/monitoring | 100% | 100% | 85%* | 100% | High | N/A – existing core role
Resource 4 | Senior AI/Data Scientist | No | Recommended 17-Aug-26 | Parallel linkage / impact development, evaluation, experimentation and remediation | 100% | 100% | 85%* | 100% | Critical | Approve from project start
Resource 5 | AI Developer / Data Scientist | No | Recommended 17-Aug-26 or 1-Oct-26 | Parallel development, prompt/retrieval, testing, documentation and capacity cover | 100% | 100% | 85%* | 100% | High | Approve phased; start before critical build bottleneck
Monitoring Team | Monitoring / Operations | External dependency | TBD | Own monitoring operations and KPI execution; Delivery supports | TBD | TBD | TBD | TBD | Critical | Named team + backup required
IT | IT / Platform | External dependency | TBD | Platform support, monitoring dashboard, integration, deployment and go-live | TBD | TBD | TBD | TBD | Critical | Named IT owner + backup + agreed response path
Capacity Planning Note
Management Case for Additional Resources
• Hard deadline: project completion by Nov 2026; schedule has no negotiation buffer.
• Delivery has two substantial AI solution tracks (Linkage + Impact Assessment) plus EDA, evaluation, SME validation, production readiness, governance and monitoring.
• One Senior AI Developer creates a technical bottleneck and single point of failure.
• The Delivery Lead is accountable for the outcome and therefore needs capacity to manage, QC, recover and intervene technically—not become the sole developer.
• October has predictable Kolkata leave impact and November has Diwali availability risk.
• Recommendation: approve two additional Data Scientist / AI Developer resources; if Management resists, at minimum approve Resource 4 for the build/evaluation phase.

## External Dependency Register
HSBC ¦ EXTERNAL DEPENDENCY REGISTER
ID | Dependency | Dependency Owner | Required By | Blocks | Trigger / Failure Condition | Impact | Preventive Control | Fallback / Recovery | Escalation Point | Status | Comments
ED01 | REGMAP data access | Data Owner | 24-Aug-26 | M2 | Access not available by 24-Aug | High | Access request and confirmation before start | Use approved extract; re-sequence non-data work; escalate | Delivery Lead + Data Owner | Open
ED02 | Helios data access | Data Owner | 24-Aug-26 | M2 | Access not available by 24-Aug | High | Pre-book access confirmation | Approved extract / alternate source if available | Delivery Lead + Data Owner | Open
ED03 | Historical linked-alert / labelled data | Business/SME Data Owner | 4-Sep-26 | M4 | Insufficient linked examples | Critical | Treat as Day-1 dependency; quantify required population early | Formal limitation decision; do not claim credible baseline/evaluation without evidence | Delivery Lead + Sponsor | Open
ED04 | SME availability – Linkage | SME Lead | 5-Oct-26 | M5 | No named SME / no slot | Critical | Book validation slots in Aug; named backup SME | Delegate SME; sponsor escalation; re-sequence remediation but protect gate | Delivery Lead + Sponsor | Open
ED05 | SME availability – Impact Assessment | SME Lead | 5-Oct-26 | M7 | No named SME / no slot | Critical | Book validation slots in Aug; named backup SME | Delegate SME; sponsor escalation | Delivery Lead + Sponsor | Open
ED06 | AI platform availability | Platform Owner | 7-Sep-26 | M3/M6 | Platform unavailable > agreed service window | High | Confirm support route; maintain test artefacts/cached data | Offline testing; approved alternate endpoint/environment if available | Delivery Lead + Platform Owner | Open
ED07 | API availability / quota | API / Platform Owner | 7-Sep-26 | M3/M6 | API errors, quota or outage | High | Quota check and monitoring | Cached responses for test cases; alternate approved API/model if available | Russel + Platform Owner | Open
ED08 | Compute / server availability | Platform Owner | 7-Sep-26 | M3 | Server unavailable / jobs blocked | High | Capacity reservation / support contact | Approved alternate compute; queue/retry; re-sequence experiments | Russel + Platform Owner | Open
ED09 | Monitoring Team capacity | Monitoring Team Lead | 12-Oct-26 | M9 | No team or no named owner | Critical | Secure named team in Aug | Sponsor escalation; interim manual monitoring only if formally accepted | Delivery Lead + Sponsor | Open
ED10 | IT monitoring dashboard | IT Owner | 15-Oct-26 | M9 | Dashboard not available by 30-Oct | High | Agree IT build plan and acceptance date | Manual monitoring interim only if governance permits; escalate IT delivery | Delivery Lead + IT GHead | Open
ED11 | Governance reviewer availability | Governance Owners | 12-Oct-26 | M10 | Review slot unavailable / turnaround delayed | High | Pre-book reviewers and review windows | Escalate to governance lead; parallelise documents | Delivery Lead + Governance Lead | Open
ED12 | Model Sponsor availability for AIRCO | Model Sponsor | 19-Oct-26 | M10 | Sponsor unavailable for walkthrough/handover | High | Pre-book sponsor session; prepare spoon-fed pack | Delegate if governance permits; sponsor escalation | Delivery Lead + Sponsor's Manager | Open
ED13 | IT deployment readiness | IT GHead / IT Owner | 2-Nov-26 | M11/M12 | IT environment not ready | High | Deployment readiness checkpoint | IT recovery plan; Delivery support only | IT GHead | Open

## RAID Log
HSBC ¦ RAID LOG
ID | Type | Description | Workstream / Milestone | Probability | Impact | Severity | Owner | Mitigation / Response | Target Date | Status | Escalation Needed?
R01 | Risk | Insufficient historical linked-alert / labelled data prevents credible baseline and evaluation | M2/M4 | High | High | Critical | Delivery Lead | Escalate as Day-1 dependency; quantify minimum data need; formal decision if unavailable | 4-Sep-26 | Open | Yes
R02 | Risk | SME unavailable for validation/sign-off | M5/M7 | Medium | High | Critical | Delivery Lead | Pre-book slots + backup SME + sponsor escalation | 5-Oct-26 | Open | Yes
R03 | Risk | Platform/API/server outage disrupts development | M3/M6 | Medium | High | High | Russel | Fallback test artefacts, alternate approved environment, incident escalation and re-sequencing | 7-Sep-26 | Open | Yes
R04 | Risk | October leave reduces Kolkata team capacity | M5-M10 | High | Medium | High | Delivery Lead | Front-load critical validation; confirm leave; protect post-Puja recovery capacity | 1-Oct-26 | Open | Yes
R05 | Risk | Diwali availability reduces November support capacity | M11/M12 | Medium | Medium | Medium | Delivery Lead | Agree support rota and IT ownership before Nov | 1-Nov-26 | Open | No
R06 | Risk | Monitoring team not available | M9 | Medium | High | Critical | Delivery Lead | Secure named Monitoring Team in Aug; escalate capacity gap | 12-Oct-26 | Open | Yes
R07 | Risk | IT monitoring dashboard delayed | M9 | Medium | High | High | IT Owner | Baseline dashboard delivery plan; interim monitoring only if formally approved | 15-Oct-26 | Open | Yes
R08 | Risk | Governance documentation becomes end-loaded | M10 | Medium | High | High | Delivery Lead | Create evidence/documentation alongside development and validation | 12-Oct-26 | Open | Yes
R09 | Risk | One Senior AI Developer becomes single point of failure | M3-M8 | High | High | Critical | Delivery Lead | Request Resource 4/5; cross-train; protect Russel's capacity | 17-Aug-26 | Open | Yes
R10 | Risk | Hard Nov deadline leaves no recovery buffer | All | High | High | Critical | Delivery Lead | Use weekly critical-path review and recovery triggers from Day 1 | 17-Aug-26 | Open | Yes
I01 | Issue | [8 empty] | Open | No
A01 | Assumption | Required project data, platform access and governance routes will be available as planned | M1-M2 | Medium | High | High | Delivery Lead | Validate assumptions by 21-Aug; convert failed assumptions to dependencies/issues | 21-Aug-26 | Open | Yes

## Governance Tracker
HSBC ¦ GOVERNANCE TRACKER
Gate | Governance Item | Documentation Activity | Evidence / Inputs Required | Accountable Owner | Reviewer / Approver | Start | Target Complete | Dependency | Status | Escalation / Recovery | Comments
GOV1 | ASDA | Create ASDA document; maintain evidence; submit; track comments | Scope, solution, evaluation, controls | Delivery Lead | ASDA reviewer | 12-Oct-26 | 19-Oct-26 | Solution evidence | Not Started | Pre-book reviewer; escalate turnaround
GOV2 | Monitoring | Create monitoring document / KPI pack | KPIs, thresholds, ownership, monitoring design | Delivery Lead + Monitoring Team | Governance / Monitoring reviewer | 12-Oct-26 | 21-Oct-26 | M9.1/M9.2 | Not Started | Draft in parallel; named Monitoring Team
GOV3 | MDT | Create MDT documentation and evidence pack | Model/evaluation/governance evidence | Delivery Lead | MDT | 19-Oct-26 | 23-Oct-26 | M4/M5/M7 | Not Started | Pre-book review; delegate if permitted
GOV4 | ToR | Create Terms of Reference | Scope, roles, governance and operating model | Delivery Lead | Relevant governance owner | 19-Oct-26 | 23-Oct-26 | Governance route | Not Started | Template prepared early
GOV5 | QMIO | Create QMIO documentation and supporting evidence | Model/solution/evaluation/control evidence | Delivery Lead + relevant owner | QMIO | 19-Oct-26 | 28-Oct-26 | Evaluation + governance evidence | Not Started | Pre-book review and track comments daily
GOV6 | AIRCO | Create AIRCO document / pack | Full model, risk, controls, evidence, decisions and ownership | Delivery Lead | Model Sponsor / AIRCO | 19-Oct-26 | 28-Oct-26 | All major evidence | Not Started | Sponsor slot booked; spoon-fed walkthrough; action tracker
GOV7 | AIRCO | Model Sponsor handover / walkthrough | Spoon-feed sponsor: explain document, decisions, evidence, responsibilities and open actions | Delivery Lead | Model Sponsor | 26-Oct-26 | 30-Oct-26 | GOV6 | Not Started | Backup sponsor delegate / management escalation if unavailable
GOV8 | IMR | Create/compile IMR documentation and evidence | Required IMR evidence | Delivery Lead + relevant owners | IMR reviewers | 19-Oct-26 | 30-Oct-26 | All applicable evidence | Not Started | Pre-book reviewer slots

## Monitoring & Handover
HSBC ¦ MONITORING & HANDOVER
Item | Owner | Delivery Team Responsibility | External Team Responsibility | Start | Target | Dependency | Exit Criteria | Status | Recovery if Delayed
KPI definition | Delivery Lead + Monitoring Team | Support KPI definition and confirm solution-specific signals | Monitoring Team owns operational KPI definition/monitoring | 12-Oct-26 | 16-Oct-26 | Monitoring Team availability | KPIs, thresholds and ownership agreed | Not Started | Escalate capacity; named backup
Monitoring document | Delivery Lead + Monitoring Team | Create/support document | Monitoring Team reviews/accepts operational process | 15-Oct-26 | 21-Oct-26 | KPI definition | Approved monitoring document | Not Started | Draft in parallel
Monitoring dashboard | IT | Provide requirements, validate output | IT builds and owns dashboard | 15-Oct-26 | 30-Oct-26 | KPI definition + IT capacity | Dashboard built and validated | Not Started | Escalate IT; interim manual monitoring only if approved
Monitoring handover | Monitoring Team | Provide model/solution context and support | Monitoring Team accepts operational ownership | 26-Oct-26 | 30-Oct-26 | Dashboard + document | Named operational owner and backup | Not Started | Sponsor/operations escalation
Deployment | IT | Provide support/back-up; clarify technical/business issues | IT owns deployment and go-live | 2-Nov-26 | 13-Nov-26 | M8/M9/M10 | IT confirms deployment complete | Not Started | IT recovery plan; Delivery does not own deployment execution
Post-go-live support | Delivery Lead + Russel | Support, troubleshoot and validate | IT/Monitoring own operational processes | 9-Nov-26 | 20-Nov-26 | Successful deployment | Open critical issues owned; support transition complete | Not Started | Escalate material production issue through IT/governance

## Assumptions & Calendar
HSBC ¦ ASSUMPTIONS & CALENDAR
Item | Type | Date / Window | Planning Treatment | Owner | Status | Action Required
Project start | Baseline | 17-Aug-26 | Hard start date | Delivery Lead | Confirmed | Baseline
Project completion | Constraint | Nov 2026 | Hard deadline; exact contractual date to be confirmed | Delivery Lead | Open | Confirm exact date
Durga Puja capacity reduction | Capacity Risk | Oct 2026 | Reduce Kolkata team availability; front-load SME validation and critical development | Delivery Lead | Planned | Confirm exact leave dates for user + Russel
Diwali capacity reduction | Capacity Risk | Nov 2026 | Plan support rota and avoid relying on full team availability around Diwali | Delivery Lead | Planned | Confirm exact leave dates
SME validation slots | Dependency | 5–9 Oct | Must be booked in Aug, not assumed later | Delivery Lead | Open | Secure named SME + backup
Monitoring Team availability | Dependency | 12–30 Oct | Must be confirmed before monitoring work starts | Delivery Lead | Open | Secure named team + backup
IT dashboard capacity | Dependency | 15–30 Oct | IT-owned build; Delivery validates | IT Owner | Open | Confirm IT owner and plan
IT deployment ownership | Scope boundary | Nov 2026 | IT owns deployment/go-live; Delivery support only | IT GHead / IT Owner | Confirmed | Document RACI
Additional Resource 4 | Resource Ask | 17-Aug-26 | Recommended to protect parallel AI development/evaluation | Management | Open | Approve
Additional Resource 5 | Resource Ask | 17-Aug-26 or 1-Oct-26 | Recommended to reduce bottleneck and cover capacity | Management | Open | Approve / phase

## RACI
HSBC ¦ RACI
Deliverable / Decision | Delivery Lead | Russel – Senior AI Developer | Junior Data Scientist / AI Developer | Additional AI/Data Scientist | Monitoring Team | IT | SME | Model Sponsor
Overall delivery | A/R | C | C | C | I | C | C | I
Scope / baseline | A/R | C | C | I | I | I | C | C
EDA / data readiness | A | R | R | C | I | C | C | I
Linkage solution | A | R | C | R | I | C | C | I
Impact assessment solution | A | R | C | R | I | C | C | I
Evaluation / method selection | A/R | R | C | R | I | I | C | C
SME validation | A/R | C | C | C | I | I | R | C
Production code/documentation | A | R | R | C | I | C | I | I
Monitoring KPI/process | A | C | C | C | R | C | I | I
Monitoring dashboard | C | C | C | C | R | A/R | I | I
Governance documentation | A/R | C | C | C | C | C | C | C
AIRCO sponsor handover | A/R | C | C | C | I | I | I | R
Deployment / Go-live | C | C | I | I | I | A/R | I | I
Post-go-live support | A/R | R | C | C | C | R | C | I

## Critical Path
HSBC ¦ CRITICAL PATH
Sequence | Milestone / Gate | Target End | Must Happen Before | Primary Owner | Failure Impact | Recovery Trigger | Recovery Action
1 | M1 Scope & baseline | 21-Aug-26 | M2 | Delivery Lead | Schedule baseline unstable | Scope not signed by 21-Aug | Escalate; freeze decisions; protect downstream dates
2 | M2 Data Readiness | 4-Sep-26 | M3/M4/M6 | Senior Data Scientist | Development/evaluation blocked | Critical data unavailable or quality unacceptable | Escalate data owner; use approved extract; formal limitation decision
3 | M3 Linkage Build | 25-Sep-26 | M4 | Russel | Method selection compressed | Candidate solution not evaluation-ready | Add resource / re-sequence / cut non-critical experiments
4 | M4 Method Selection | 2-Oct-26 | M5 | Delivery Lead | SME validation cannot start | No evidence-based method selected | Decision escalation; use pre-agreed decision forum
5 | M5 Linkage SME Sign-off | 9-Oct-26 | M8 | Delivery Lead | Production readiness blocked | SME absent / material unresolved findings | Backup SME / sponsor escalation / protected remediation
6 | M7 Impact SME Sign-off | 9-Oct-26 | M8 | Delivery Lead | Production readiness blocked | SME absent / material unresolved findings | Backup SME / sponsor escalation / protected remediation
7 | M8 Production Readiness | 23-Oct-26 | M11 | Russel | IT cannot prepare deployment | Code/KT/documentation incomplete | Parallelise documentation; add AI developer capacity
8 | M9 Monitoring Readiness | 30-Oct-26 | M11 | Monitoring Team + IT | Governance/deployment readiness impacted | Monitoring team/dashboard delayed | Escalate; interim process only if formally approved
9 | M10 Governance | 30-Oct-26 | M11 | Delivery Lead | Deployment cannot proceed | Reviewer delay/document gap | Parallel reviews; escalate governance owner
10 | M11 Deployment Readiness | 6-Nov-26 | M12 | IT | Go-live slips | Environment not ready | IT recovery plan; Delivery supports
11 | M12 Go-Live | Nov-26 | Project completion | IT | Hard deadline threatened | Deployment failure | IT incident/recovery plan; Delivery supports and validates

## Management Resource Ask
HSBC ¦ MANAGEMENT RESOURCE ASK
DECISION NEEDED
OPTION | TEAM | DELIVERY CONFIDENCE | PRIMARY RISK | RECOMMENDATION
A | 3 core | Low / fragile | Russel becomes technical bottleneck; parallel work becomes serial; leave + external dependencies create no recovery capacity | Do not recommend
B | 4 people | Medium–High | Still limited capacity for parallel Linkage + Impact + production/governance support | Minimum acceptable
C | 5 people | High | Requires management approval but gives parallel AI delivery capacity and recovery resilience | RECOMMENDED
WHY 5?
• Two major AI solution tracks need to progress in parallel.
• Russel is the only confirmed Senior AI Developer and is a single point of technical failure.
• The Delivery Lead must own end-to-end delivery/QC and retain capacity for intervention, not become the default developer.
• October Kolkata leave reduces effective capacity; November Diwali creates further availability risk.
• SME, platform/API/server, Monitoring Team, IT dashboard and governance are external dependencies that can consume schedule buffer.
• Hard Nov deadline means recovery capacity must exist before a problem occurs.
NAMING CONVENTION